## Sheet1
Project Phase | Item | Description | Data required | Input Required | Definition of Done | Min Days | Expected Days | Maximum Days
Judge name extraction from court roll | Web-scraping of all court roll PDFS | The SCA has court rolls in PDF with the information that we need:http://www.justice.gov.za/sca/roll/roll_archive.html The Constitutional Court Roll on SAFLII doesn't include judge names. But there may be some on justice.gov These court rolls need to be scraped. | Court rolls with case names and judge names. | Might be necessary to talk to court registrars. If so, whoever is on first name basis. | Court rolls for at least 2 years for a court other than the CC downloaded from internet. | 2 | 6 | 12 |  | Notes:
| PDF to text conversion | This should be relatively straightforward if the PDFs are of sufficient quality. Otherwise, we will either have to make use of the existing OCR pipeline, or pipe through the Google Vision API. | None | Mariya and her OCR team, potentially. | All data collected is available as .txt files, with minimal errors due to OCR. | 2 | \ | 12 |  | Who is the acting judge (get judge abbreviations)
| Database schema design and implementation, API, data upload. | Text should be made available in a database. This will require setting up a database, creating a schema, creating an API, and uploading the data. I will only use a local db for the POC. | None | None | All data collected is available from a database. | 1 | 2 | 3 |  | Attorney and counsel names.
| Extraction of judge names and cases asigned to them, dates. | Standard regular expression work. | None | None | Every case has a judge, date and case name associated to it in the database. Case names are atomised into party, counter party etc. | 4 | 8 | 32 | (depends on standardisation of the format of the court roll. I expect that, at least for 1 court, it should be fairly standard). | counsel -> race gender.
| Linking of cases names with cases in our db | In order to get the full text of the judgment, we will need to link case names with our records of cases. This requires a fuzzy-matching of the case name on the court role and the case name as it appears in our database. Of course, I've already written a module to do this, so it will just need to be appropriately adapted for the court rolls | CC judgments (Pocketlaw), with decently formatted metadata fields. | Help in accessing the correct data from SAFLII | At least 85% of cases where all data was present on the court roll and the case is available on Pocketlaw, should successfully be matched with the appropriate case. | 4 | 4 | 12 |  | Bar listings.
Judge name extraction from CC Judgments. | Extraction of judge names from the linked judgments | Extracting judge names from each page of the judgment. Standard regular expression work. | CC Judgments | None | At least 90% of pages in database that have a judge name on them, should have those names successfully extracted | 2 | 8 | 16 | Might be as simple as taking the first word. But very likely to be more complex and have many edge cases. | Hope and Nicole sent spreadsheet from Justice. Try and put in race and gender.
[5 empty] | total | 15 | 28 | 87
Things not included in the POC (will be needed if POC is success, not worth doing before testing whether the process will work). | Visualisation of results
production environment setup
Web page for results
More than 1 court
Accuracy >=95%
Ability to run as service (process will have to be started manually whenever new data is inputted)